## Skillset
TASK | TYPE | Owner | ETA | Status | Update | Comment
Terraform Code to Build Jenkins Server | Terraform | Seun | 2 weeks | TO DO
Git hook to force checks before “push” The following must be fulfilled 1] User must add comment to every commit. 2]Comment must nit be less than 20 characters 3]Comment must end with “BY Tope” 4] Artefacts change must not have sensitive data e.g AWS credentials | GIT | Tope | 2 weeks | TO DO
Simple NodeJS code (web) that can write and read from MongoDB | NODEJS | Lolade | 1 week | IN PROGRESS |  | Created stub to help with getting started Artefacts in codebase directory
Docker Compose to spin up Mongo Instance and NodeJS to help with APP testing and developmennt | Docker | Segun | 1 week | DONE
Work on initial Frontend design for the web interface | HTML | Lolade/Segun |  | IN PROGRESS
Quick study of Angular JS | Study |  |  | TO DO
Directory structure organization of the artefacts | Misc | Segun | 1 day | DONE